## Sheet1
Phase | Task | Start Date | End Date | Assignee | Deliverable
Requirement Gathering | Collect requirements from stakeholders | 01-Aug-2024 | 07-Aug-2024 | Sarah Lee | Requirements document
Requirement Gathering | Document requirements | 07-Aug-2024 | 14-Aug-2024 | Sarah Lee | Requirements document
Design Phase | Create UI/UX designs | 15-Aug-2024 | 22-Aug-2024 | Mia Chen | Design mockups
Design Phase | Develop prototypes | 22-Aug-2024 | 29-Aug-2024 | Mia Chen | Prototypes
Development Phase | Implement new features | 01-Sep-2024 | 10-Sep-2024 | Alex Johnson | New feature code
Development Phase | Enhance existing features | 10-Sep-2024 | 20-Sep-2024 | Rahul Patel | Enhanced features code
Development Phase | Code review and integration | 20-Sep-2024 | 29-Sep-2024 | Emma Brown | Integrated codebase
Testing Phase | Conduct comprehensive testing | 30-Sep-2024 | 13-Oct-2024 | Emily Davis | Test reports and bug fixes
Deployment | Deploy updates to app and watch | 14-Oct-2024 | 20-Oct-2024 | Rahul Patel | Deployed features
User Feedback Integration | Collect and analyze user feedback | 21-Oct-2024 | 27-Oct-2024 | David Nguyen | Feedback report and improvements